INNOVATION & ECONOMIC COMPETITIVENESS INITIATIVE

IECI

West Africa Multi-Hub Innovation & Industrial Ecosystem

Investor Brief

A Program of I&DP — Innovation and Development Platform for Africa

Under LF Holdings, LLC  ·  Sponsored by DAKIMO Investment

STRICTLY CONFIDENTIAL — FOR QUALIFIED INVESTORS ONLY

partnerships@lf-hold.com  ·  lf-hold.com  ·  +1 (307) 226-1876

PROGRAM AT A GLANCE

IECI — Key Investment Metrics

| $137.6M Total Program CAPEX | 18.4% Blended Program IRR | 12 Innovation Hubs (12 Departments) | 60,000+ Direct Jobs Created |
| --- | --- | --- | --- |

| $4–6B Projected GDP Impact (10 years) | 24.3% DAKIMO Equity IRR (Direct) | 31.2% DAKIMO All-In Economic IRR | Year 4 Hub-Level Break-Even |
| --- | --- | --- | --- |

EXECUTIVE SUMMARY

The Opportunity in One Sentence

INVESTMENT THESIS IECI is a government-backed, DFI-financed network of 12 innovation and agro-industrial hubs across Benin's 12 departments — designed to transform the country's commodity-export economy into a value-added processing and technology manufacturing powerhouse, creating 60,000+ direct jobs and $4–6B in GDP impact over 10 years, while delivering an 18.4% blended IRR to private co-investors.

Benin is at an inflection point. The government has committed $35B+ under its Government Action Program (PAG I & II), GDP is growing at 7.5% annually, and the Glo-Djigbé Industrial Zone (GDIZ) has already demonstrated the model — creating 14,000+ jobs since inception. IECI replicates and scales this model across all 12 departments, targeting sectors from cassava and cashew processing to aquaculture, leather goods, and technology manufacturing.

What makes IECI structurally different from typical development programs: it is not a grant. It is a Build-Operate-Transfer (BOT) public-private partnership where private investors hold equity in Hub SPVs, earn processing royalties, lease revenues, and carried interest on SME portfolio exits — while the government provides land, infrastructure connections, and regulatory incentives.

Why Now

Benin's 2026 presidential transition creates a narrow window to secure program architecture and anchor investor commitments before a new administration re-prioritizes its development agenda. IECI is positioned as an apolitical economic competitiveness program with cross-party appeal — backed by DFI endorsements that survive government transitions. The window to enter as a foundational co-investor closes in 2026–2027.

PROGRAM ARCHITECTURE

Structure & Legal Framework

Entity Structure

| IECI National Authority (INA) | Public Establishment (EPIC) — Republic of Benin. Sovereign program vehicle; holds land rights; issues government guarantees; DFI counterpart. |
| --- | --- |
| Program Management Unit (PMU) | Subsidiary SA — Cotonou, Benin. Operational management, procurement, monitoring & evaluation, technical assistance contracting. |
| Hub SPVs (×12) | One SARL per department — Asset-holding, revenue collection, local PPP governance, hub P&L accountability. |
| IECI Diaspora Bond Vehicle | Special Purpose Vehicle (OHADA). Issuance and administration of 5-year Diaspora Innovation Bonds. Ring-fenced from PMU. |
| DAKIMO Investment | LLC — Wyoming, USA. Technical assistance, international fundraising, brand and IP, global investor liaison. Founding Technical Sponsor & Co-Investor. |

PPP Framework

Each hub is structured as a Build-Operate-Transfer (BOT) variant: government provides land and public infrastructure (roads, utilities), while private partners finance and operate hub facilities under a 25-year concession. At Year 25, infrastructure reverts to the state while the private entity retains its SME portfolio companies.

Hub SPV equity split: 30% INA (government), 40% anchor private investors, 20% DAKIMO/PMU, 10% departmental municipality.

12-Hub Geographic Coverage

One hub per department, each anchored to the department's primary agricultural and industrial comparative advantage:

| Zou | Cassava processing, pineapple, palm oil — Pilot Hub 1 |
| --- | --- |
| Borgou | Cashew, cotton ginning, shea butter — Pilot Hub 2 |
| Atlantique | Aquaculture (tilapia), tomato paste, tech assembly — Pilot Hub 3 |
| Atacora | Black fonio (premium export), hibiscus, organic cotton |
| Alibori | Moringa processing, gum arabic, sesame |
| Collines | Yam value chain, soybeans, cassava starch |
| Couffo | Vetiver essential oil, palm kernel processing |
| Donga | Wood value-added products, charcoal alternatives |
| Littoral / Cotonou | Black soldier fly protein, logistics & packaging hub |
| Mono | Artisanal sea salt, seaweed cultivation, shrimp |
| Ouémé | Turmeric & ginger processing, rice milling |
| Plateau | Citrus processing, mango drying, cashew kernel |

FINANCIAL SUMMARY

Returns & Capital Structure

Program CAPEX — $137.6M Total

| Phase 0 — Setup (2026) | $2.4M — PMU establishment, legal, feasibility, anchor LOIs |
| --- | --- |
| Phase 1 — 3 Pilot Hubs (2027–2028) | $25.4M — Zou, Borgou, Atlantique (CAPEX per hub: ~$8.47M) |
| Phase 2 — 6 Hubs (2029–2031) | $50.8M — Atacora, Alibori, Collines, Couffo, Donga, Ouémé |
| Phase 3 — 3 Hubs (2032–2034) | $25.4M — Plateau, Mono, Littoral expansion |
| SME Seed Fund | $12.0M — Equity seed capital for 2,400 SMEs across all hubs |
| Working Capital Reserve | $8.0M — PMU operations, contingency, DFI compliance |
| Total | $137.6M over 8 years |

Capital Sources

| AfDB / IDA Sovereign Loan (35%) | $48.2M — On-lending to Hub SPVs against government guarantee |
| --- | --- |
| IFAD / FAO Concessional Financing (20%) | $27.5M — Agricultural processing components, soft terms |
| Anchor Private Investors (30%) | $41.3M — PE funds, diaspora capital, strategic industrialists |
| Diaspora Innovation Bonds (10%) | $13.8M — 5-year bonds, 7% coupon, BCEAO-compliant |
| DAKIMO Co-Investment (5%) | $6.9M — Equity + bridge; $3.6M in direct Hub SPV stakes |
| Government In-Kind (land + infra) (n/a) | ~$27.5M value — land title transfer + public infrastructure |

Investor Returns (Base Case)

| Anchor Private Investor IRR | 22–26% — equity in Hub SPVs, processing royalties, lease income |
| --- | --- |
| Blended Program IRR | 18.4% — across all capital sources weighted |
| DAKIMO Equity IRR (direct stake) | 24.3% — base; 30.1% optimistic |
| DAKIMO All-In Economic IRR | 31.2% — equity + management fees + carry + IP replication |
| Hub-Level Break-Even | Year 4 (base); Year 3.1 (optimistic); Year 4.5 (conservative revised) |
| Benefit-Cost Ratio (govt. investment) | 3.4× (Year 5) → 19.9× (Year 10, as hubs mature) |
| DAKIMO Total Economic Stake (Year 10) | $11.5M–$18.9M on $3.6M deployed (4.1× base / 314% ROI) |

NOTE ON FINANCIAL PROJECTIONS Financial figures are modeled using DFI-standard conventions and regional benchmarks (Rwanda SEZs, Ethiopian Hawassa IP, GDIZ Benin, World Bank West Africa Competitiveness Program). They represent investment-grade planning estimates, not audited forecasts. Full financial model with assumption sources, validation roadmap, and sensitivity analysis available in the complete IECI Investment Proposal — available to qualified investors on request.

SPONSORING ENTITY

DAKIMO's Role & Alignment

DAKIMO Investment (a subsidiary of LF Holdings, LLC) serves as Founding Technical Sponsor and Co-Investor. This is not a passive advisory role — DAKIMO has structural incentives tied directly to program performance:

| Direct Equity Co-Investment | 20% PMU SA stake + 5–10% direct equity per Hub SPV. $3.6M deployed over Phase 0–1, pari passu with anchor investors. |
| --- | --- |
| PMU Management Contract (10-year) | $192K/year fixed fee for technical sponsorship and PMU leadership. Paid from program operating budget, ceases if PMU is fully nationalized after Year 7. |
| Performance Bonus (KPI-linked) | $0.5M–$1.2M cumulative, triggered by hub opening milestones, job creation KPIs, DFI audit clean opinions, and first export shipment. |
| Carried Interest on SME Exits | 15% carry above 1.2× hurdle on 2,400 SME equity portfolio. Receivable from Year 5 onward. Estimated $2.5M–$5M over program life. |
| ECOWAS Replication Rights | DAKIMO retains rights to replicate the IECI model in Togo, Ghana, Niger, and Senegal — estimated $3M–$8M in advisory fees and equity stakes in successor programs. |

MARKET CONTEXT

Benin Macro & Why This Market

| GDP Growth (2024) | 7.5% — driven by port, construction, and services (IMF/World Bank) |
| --- | --- |
| Political Stability | Democratic transitions since 1990; peaceful 2026 presidential election scheduled |
| DFI Active Portfolio | IFC: $60.8M active in Benin; IFC committed EUR 20M to Benin Terminal (Nov 2024) |
| World Bank Financing | EUR 635.5M approved package (Nov 2024) — validates macroeconomic credibility |
| GDIZ Precedent | 14,000+ jobs created; $9.7B government urban infrastructure program underway |
| Investment Code Incentives | 5–8 year CIT holiday; import duty exemptions on equipment; unrestricted profit repatriation in USD/EUR |
| ECOWAS Market Access | 420M+ consumer market; Benin as gateway between Nigeria (220M) and Francophone West Africa |
| BCEAO Monetary Union | CFA franc — pegged to EUR, eliminating FX risk for European investors; stable monetary environment |

NEXT STEPS

How to Engage

The IECI program is currently in Phase 0 — program architecture finalization, anchor investor engagement, and government authorization. Investor participation is available at the following levels:

| Anchor Hub Investor ($3M–$8M per hub) | 40% Hub SPV equity stake; naming rights; anchor tenant recruitment priority; board seat on Hub SPV investment committee |
| --- | --- |
| Program Co-Investor ($1M–$3M) | Across-program exposure; participation in 3+ Hub SPVs; diaspora bond allocation; quarterly reporting |
| Diaspora Bond Investor ($50K–$500K) | 5-year bonds, 7% annual coupon, BCEAO-compliant; accessible to diaspora investors in US, France, Canada |
| Strategic Anchor Tenant | Processing plant operator or off-taker; preferential lease terms; equity co-investment option |

REQUEST THE FULL INVESTMENT PROPOSAL The complete IECI Investment Proposal (60+ pages) includes detailed financial models, assumption validation annex, agricultural sector analysis, legal structure documentation, DFI engagement strategy, and target investor profiles. Contact us to receive the full document under NDA.

Contact

| Email (Partnerships) | partnerships@lf-hold.com |
| --- | --- |
| Email (General) | contact@lf-hold.com |
| Website | lf-hold.com |
| Phone | + 1 (307) 226-1876 |
| DUPM & Co. (Deal Flow) | partnership@dupmco.com · dupmco.com |
| Operating Offices | Boston, MA · Cotonou, Benin · Abidjan, Côte d'Ivoire |

STRICTLY CONFIDENTIAL — FOR QUALIFIED INVESTORS ONLY

© 2026 LF Holdings, LLC. All rights reserved. This document is for informational purposes only and does not constitute an offer to sell or a solicitation to buy any security. Past performance is not indicative of future results. All financial projections are modeled estimates and subject to change.